## Full Gantt
Portable Solar Emergency Power Station — Revised Two-Semester Gantt Chart
Auburn University ECE Capstone • Revised after CDP technical-depth feedback • Custom design → prototype → verify → integrate
Project Task | Category | CAPSTONE 1 — FALL 2026 | [16 empty] | CAPSTONE 2 — SPRING 2027
|  | Aug 17 | Aug 24 | Aug 31 | Sep 07 | Sep 14 | Sep 21 | Sep 28 | Oct 05 Fall Break | Oct 12 | Oct 19 | Oct 26 | Nov 02 | Nov 09 | Nov 16 | Nov 23 Thanksgiving | Nov 30 | Dec 07 Finals | Jan 04 | Jan 11 | Jan 18 | Jan 25 | Feb 01 | Feb 08 | Feb 15 | Feb 22 | Mar 01 | Mar 08 Spring Break | Mar 15 | Mar 22 | Mar 29 | Apr 05 | Apr 12 | Apr 19 | Apr 26 Finals
Project definition & original CDP | Planning | ■ | ■ | ■
Faculty feedback review & scope revision | Planning |  |  |  | ■ | ■
Faculty / SME architecture & scope confirmation | Planning |  |  |  |  | ◆ | ◆
Revised system requirements & block diagram | Design |  |  |  |  | ■ | ■ | ■
MPPT topology research & selection | Power Electronics | [5 empty] | ■ | ■ | ■
MPPT calculations & circuit simulation | Power Electronics | [6 empty] | ■ | ■ | ■ | ■
MPPT schematic & component selection | Power Electronics | [8 empty] | ■ | ■ | ■
MPPT prototype construction | Power Electronics | [10 empty] | ■ | ■ | ■
MPPT control algorithm / firmware | Embedded | [9 empty] | ■ | ■ | ■ | ■ | ■
Sensor-interface circuit design | Embedded | [6 empty] | ■ | ■ | ■ | ■ | ■
Embedded controller schematic / prototype | Embedded | [9 empty] | ■ | ■ | ■ | ■ | ■
Battery / BMS architecture & safety review | Battery & BMS | [5 empty] | ■ | ■ | ■ | ■
Inverter architecture / custom-scope decision | Power Electronics | [5 empty] | ■ | ■ | ■ | ■
Procurement / PCB & prototype parts | Procurement | [8 empty] | ■ | ■ | ■ | ■
Buffer / failed prototype recovery | Buffer | [11 empty] | ■ | ■
MPPT bench testing & efficiency characterization | Testing | [12 empty] | ■ | ■ | ■ | ■
Sensor calibration & embedded bench testing | Testing | [12 empty] | ■ | ■ | ■ | ■
Semester 1 subsystem verification & documentation | Documentation | [15 empty] | ◆ | ◆
Winter break / no scheduled project work | Break | bar: CAPSTONE 2 — SPRING 2027 Jan 04 to CAPSTONE 2 — SPRING 2027 Jan 11
Semester 2 reassessment & design revisions | Design | bar: CAPSTONE 2 — SPRING 2027 Jan 11 to CAPSTONE 2 — SPRING 2027 Jan 18
PCB / prototype revision & fabrication | Power Electronics | bar: CAPSTONE 2 — SPRING 2027 Jan 18 to CAPSTONE 2 — SPRING 2027 Feb 01
AC / USB output implementation | Power Electronics | bar: CAPSTONE 2 — SPRING 2027 Jan 18 to CAPSTONE 2 — SPRING 2027 Feb 08
Power electronics + battery integration | Integration | bar: CAPSTONE 2 — SPRING 2027 Feb 01 to CAPSTONE 2 — SPRING 2027 Feb 15
Embedded control integration | Integration | bar: CAPSTONE 2 — SPRING 2027 Feb 01 to CAPSTONE 2 — SPRING 2027 Feb 22
Low-power integrated testing | Testing | bar: CAPSTONE 2 — SPRING 2027 Feb 15 to CAPSTONE 2 — SPRING 2027 Feb 22
Increasing-load & efficiency testing | Testing | [26 empty] | ■ | bar: CAPSTONE 2 — SPRING 2027 Feb 22 to CAPSTONE 2 — SPRING 2027 Mar 01
Spring Break / buffer | Break | [26 empty] | ■
Mechanical enclosure design & build | Mechanical/Thermal | [26 empty] | ■ | ■ | ■ | bar: CAPSTONE 2 — SPRING 2027 Feb 15 to CAPSTONE 2 — SPRING 2027 Mar 01
Thermal characterization & fan-control tuning | Mechanical/Thermal | [27 empty] | ■ | ■ | ■
Enclosure integration | Integration | [28 empty] | ■ | ■
Protection / fault-response verification | Testing | [29 empty] | ■ | ■
Runtime & full performance testing | Testing | [29 empty] | ■ | ■ | ■
Buffer / failure recovery | Buffer | [30 empty] | ■ | ■
Embedded refinement & calibration | Embedded | [27 empty] | ■ | ■ | ■ | ■ | ■
Bluetooth monitoring (stretch only) | Stretch | [30 empty] | ■ | ■
Formal requirements verification | Testing | [31 empty] | ■ | ■
Design freeze & demo preparation | Documentation | [32 empty] | ◆
Final report, presentation & demonstration | Documentation | [32 empty] | ■ | ■
Legend | Scheduled Work | Buffer / Stretch | Milestone / Review | Break / Finals
Key checkpoints: faculty/SME scope confirmation before inverter/BMS commitment • MPPT + sensing/controller prototypes verified by end of Capstone 1 • integrated bench prototype by Spring Week 6 • formal verification/design freeze before final demonstration

## 5-Week Status Slice
Weekly Status Report — Revised 5-Week Gantt Slice
Project Task | Category | Last 2 Weeks ← Current Week → Next 2 Weeks
|  | Aug 24 | Aug 31 | Sep 07 | Sep 14 | Sep 21
Project definition & original CDP | Planning | ■ | ■
Faculty feedback review & scope revision | Planning |  |  | ■ | ■
Faculty / SME architecture & scope confirmation | Planning |  |  |  | ◆ | ◆
Revised system requirements & block diagram | Design |  |  |  | ■ | ■
MPPT topology research & selection | Power Electronics |  |  |  |  | ■
Battery / BMS architecture & safety review | Battery & BMS |  |  |  |  | ■
Inverter architecture / custom-scope decision | Power Electronics |  |  |  |  | ■

## Schedule Notes
Item | Details
Revision basis | Schedule revised after faculty feedback that the project must emphasize team-designed circuits, embedded hardware, control algorithms, firmware, and verification rather than primarily integrating complete commercial functional modules.
Scope decision | Team-designed MPPT DC-DC converter, sensing/interface circuitry, embedded controller hardware, MPPT/monitoring firmware, and thermal-control functions are now explicit schedule deliverables.
Pending scope | Custom design requirements for the approximately 300 W inverter and LiFePO4 BMS/protection circuitry remain pending faculty/SME confirmation; the Gantt includes an early architecture/scope checkpoint before committing to those designs.
Fall 2026 | Classes begin Aug. 17; Fall Break Oct. 8–9; Thanksgiving Break Nov. 23–27; classes end Dec. 4; finals Dec. 7–11.
Spring 2027 | Classes begin Jan. 6; Spring Break Mar. 8–12; classes end Apr. 23; finals Apr. 26–30.
Auburn calendar source | https://www.auburn.edu/about/academic-calendar/
Buffer strategy | Buffer periods remain for exams, shipping delays, failed prototypes, redesigns, and troubleshooting.
Stretch feature | Bluetooth monitoring remains optional and occurs only after required power, protection, sensing, thermal, and local-display functions are stable.
Weekly report slice | The 5-week sheet currently shows Aug. 24 through Sep. 21, with Sep. 7 as the current project week for the Sep. 9 status report.